## Go, No Go Matrix
LAUNCH READINESS MATRIX
Go/NoGo Launch Decisions Definitions | Definition |  |  |  |  | Impact
🟢 Go | A "Go" decision means that all critical launch criteria have been met, key stakeholders are in agreement, and the product is approved to proceed with the launch as planned. All systems are verified, teams are prepared, and there are no outstanding issues significant enough to delay the release. |  |  |  |  | Proceed with launch: The launch activities will commence according to the established schedule.
🟡 Conditional Go | A "Conditional Go" means that the product is largely ready for launch, but there are minor, manageable outstanding issues or risks that need to be addressed either before or immediately after the launch. These conditions are documented, and there's a clear plan and the named owner is accountable for their resolution within a specific timeframe. |  |  |  |  | Proceed with Launch But... The launch can proceed, but contingent upon the fulfillment of the specified conditions. Failure to meet these conditions might escalate the situation or impact post-launch activities.
🔴 No Go | A "No Go" decision means that there are critical issues, unmet criteria, or significant risks identified that would unacceptably jeopardize the success of the product launch. These issues are substantial enough that proceeding with the launch as scheduled is deemed too detrimental. |  |  |  |  | Delay launch until critical issues are resolved The product launch is postponed. A plan to address the identified critical issues must be developed and executed. A subsequent review will be required to reassess readiness before a new launch date can be set.
Stage | Current Planned Duration | Details
GTM Access | 2 weeks | Features available and functioning properly We start testing and building all product education and most enablement content ASK Ideally, RnD documentation is ready on this date ASK Product Managers are available to answer our questions in a timely manner ASK Go/No Go typically happens here about 1 week in
Internal Readiness | 3 weeks long | Product Education documentation and training is ready for internal teams to consume. Internal teams upskill on the feature. During this time internal enablement teams will continue to build team-specific materials, refine customer comms, and customer facing materials.
Cohort 1 Live | 4 weeks long | First batch of customers are live with the new feature and we are ready to support them. Customer facing training/pendo’s/help center articles complete. Service Delivery and Support processes trained in and ready to execute.
GA / Cohort 2 Live | N/A | All customers are live with the new feature
Go/No Go Decision Matrix
STATUS DEFINITIONS
| Criteria | Stakeholder (s) | Current Status | Go | Conditional Go | No Go | If Conditional, Please elaborate
Executive Summary & Strategic Foundation | Business Justification | ELT |  | Clear goal, purpose, value proposition, and customer user stories documented with strategic outcome defined | Business case mostly clear but some strategic elements need refinement | Unclear business goal, purpose, or value proposition
| Market Position & Timing | ELT |  | Market analysis complete, competitive positioning clear, customer expectations align with delivery | Market analysis done but positioning needs validation | No market analysis or misaligned customer expectations
| Customer Impact Assessment | ELT |  | Ideal customer profile defined, install base adoption estimate provided, promised timeline commitments documented | Customer profile mostly defined but adoption estimates need validation | No clear customer profile or unrealistic adoption expectations
| Revenue & Risk Analysis | ELT |  | Revenue forecast and at-risk revenue clearly defined, pricing strategy established | Financial projections mostly complete but some elements under review | No revenue analysis or significant at-risk revenue unclear
| Feature Completeness | ELT |  | Feature set complete and provides compelling value for adoption, aligns with original customer user story | Feature provides adequate value but may need enhancement roadmap | Feature incomplete or insufficient value to drive adoption
| Criteria | Stakeholder (s) | Current Status | Go | Conditional Go | No Go | If Conditional, Please elaborate
Product Management & Documentation Foundation | PM Documentation Completeness |  |  | Business context, value statements, personas, use cases, mockups, troubleshooting, workarounds, steps on how to set up (or for existing customers - how to change their configuration), intended usage and affected areas fully documented per checklist standards. Indication if original elements were left out of this release. | 90%+ of required documentation complete with minor gaps identified and timeline for completion | Critical PM documentation missing or significantly below standard depth
| Cross-Feature Impact Analysis |  |  | All downstream impacts documented including configuration changes, permission updates, integration effects, and adoption steps | Impact analysis complete but some minor downstream effects need validation | Underestimation of enablement effort or undocumented feature interactions
| Feature is made available to post sale enablement functions |  |  | Post-sale enablement functions have access to the product/feature and are able to test it as part of the launch preparation process | Post-sale enablement functions have limited access to the product/feature and are able to test it as part of the launch preparation process | Post-sale enablement functions do not have access to the product/feature and are able to test it as part of the launch preparation process
| Feature Functionality |  |  | All expected functionality delivered, no core features removed from scope that would compromise the viability of the feature set | Minor functionality removed but core value maintained | Critical functionality removed eliminating customer value
| Quality Assurance |  |  | QA testing aligned with actual feature use, landing goals achievable with current quality | QA mostly aligned but some use cases need additional validation | QA testing inadequate or not aligned with real-world usage
| Designed for Customer Product Self-Enablement (where possible) |  |  | Product is designed in a way that the customer can easily enable a feature without the help of a ClearCompany human | Product cannot be enabled via self-service. However, a plan has been developed to help ClearCompany post sale team to implement the product in an easy, seamless way. | Product cannot be enabled via self-service. There is not a clear plan and/or an easy way to implement the product without using substantial ClearCompany humans
| Third-Party Dependencies |  |  | All integrations working properly, third-party support issues resolved | Minor integration issues with workarounds available | Critical third-party dependencies not working or unsupported
| Performance & Reliability |  |  | Feature performs as expected, customers can tell if it's working properly | Performance mostly adequate but some monitoring gaps | Performance issues or customers cannot assess feature health
| Measurement & Reporting |  |  | Reporting created to measure contracted, adoption and usage in a dashboard. Success metrics for the launch are defined | Success metrics for the launch are defined but reporting/measurement capabilities mostly in place but some metrics need refinement | No success metrics are defined and/or reporting/measurement is less than adequate
| User Experience Quality |  |  | Feature intuitive for target customer, can be used without assistance on first try | Feature mostly intuitive but may need minor guidance or documentation | Feature requires significant assistance or training for first use
Enablement & Training Readiness | Overall Product Education Signoff | Sam
| Content & Training Needs | Sam |  | Customer can learn feature through short video or article, minimal content creation required | Customer needs course-level training but materials available | Extensive training required or inadequate learning materials
| Product Education Materials | Sam |  | Comprehensive training materials ready for all customer-facing teams including complete workflows. This includes but is not limited to pendo and help center articles | Most training materials ready with minor gaps in specific scenarios | Insufficient training materials or incomplete workflows
| Team-Specific Enablement (when appropriate) | Sam |  | Customized enablement materials for Sales, Support, Implementation, and Customer Success teams | Generic materials available but team-specific customization in progress | No team-specific enablement materials
| Gap Filling for Enhanced Features | Sam |  | For major enhancements to existing features, comprehensive documentation updates and training completed | Documentation updates in progress with clear timeline | Existing feature enhancements lack proper documentation updates
Customer Support Readiness | Overall Support Signoff | Michael
| Support Scalability | Michael |  | No expected increase in support volume and self-service options are available | Some exected increase in support volume but manageable and expected to decrease in a reasonable amount of time or self-service options will alleviate volume | High support volume expected or inadequate self-service options
| Support Tools & Documentation | Michael |  | Documentation is clear and includes possible error definitions | Some documentation is available to assist support in possible issues | Inadequate support tools or poor error documentation
Implementation Scale & Customer Adoption | Overall Implementation Signoff | Victoria
| Implementation Effort vs. Value | Victoria |  | Implementation effort reasonable compared to feature value and business impact | Effort mostly reasonable but some efficiency improvements needed | Implementation effort disproportionate to feature value
| Customer Content & Data Requirements (where applicable) | Victoria |  | Feature includes sufficient user content for use, reasonable data entry/setup required | Most content ready but some customer input needed for full value | Significant content creation or data entry required from customer
| Setup & Configuration | Victoria |  | Feature easy and quick to set up with zero or limited ClearCompany staff guidance required | Setup mostly straightforward but may need some staff assistance | Complex setup requiring significant staff support
| Customer Self-Sufficiency | Victoria |  | Customer can troubleshoot errors independently, feature works with minimal ongoing maintenance | Customer can handle most issues but some support may be needed | Customer requires ongoing staff support for basic operations
| Migration Complexity | Victoria |  | No migration required or total migration effort cost is reasonable and planned | Migration needed but cost and effort are manageable | Migration cost/effort unreasonable or poorly planned
| Cross-Department Dependencies | Victoria |  | Implementation team can execute efficiently without extensive other department support | Some cross-department coordination needed but manageable | Heavy dependency on other departments or external software
| Implementation Timeline Impact | Victoria |  | Feature doesn't extend implementation time significantly, learning curve manageable | Minor implementation timeline extension with clear mitigation | Significant implementation timeline extension
Customer Success & Ongoing Adoption | Overall CSM Signoff | Gina
| Adoption Measurement | Gina |  | Can measure adoption and usage in customer success platform, success metrics defined | Measurement capabilities mostly in place but some metrics need refinement | No adequate adoption measurement or success metrics
| Ongoing Education Requirements | Gina |  | Feature requires minimal ongoing education, customer can use repeatedly without retraining | Some ongoing education needed but manageable and scalable | Extensive ongoing education required for continued use
| Customer Value Realization | Gina |  | Feature delivers on strategic outcomes, reduces clicks/admin time, increases HR operation efficiency | Feature provides value but some efficiency gains need validation | Unclear value realization or doesn't improve customer efficiency
| Feature Enhancement Roadmap | Gina |  | No immediate feature enhancement requests anticipated, or clear roadmap exists | Some enhancement requests expected but manageable roadmap | High likelihood of immediate enhancement requests without clear plan
| Customer Expectation Management | Gina |  | Clear communication about feature maturity (V1/Beta/MVP if applicable), realistic timeline expectations | Mostly clear expectations but some maturity communications need refinement | Unclear customer expectations or maturity level
| Churn Risk Management | Gina |  | Feature reduces churn risk, doesn't remove functionality customers currently use | Feature neutral on churn risk with minor functionality changes | Feature may increase churn risk or removes valued functionality
Sales Enablement
| Sales Materials | Ryan/Jesse |  | Complete sales deck, battle cards, ROI calculator, competitive analysis ready with clear value proposition messaging | Most materials ready, missing 1-2 non-critical items | Core sales materials incomplete or value proposition unclear
| Pricing & Packaging | Ryan/Jesse |  | Final pricing approved, bundling vs. standalone pricing clear, customer purchase requirements documented | Pricing finalized but packaging details being refined | Pricing strategy not finalized or customer purchase requirements unclear
| Feature Positioning | Ryan/Jesse |  | Sales team can clearly articulate strategic value to customers, differentiation from competition established | Positioning mostly clear but some competitive differentiation needs work | Unclear positioning or weak competitive differentiation
| Demo & Proof of Concept | Ryan/Jesse |  | Stable demo environment, realistic scenarios, feature demonstrates compelling value in customer context | Demo environment available but may need scenario refinement | Demo environment unreliable or doesn't demonstrate clear value
| Recorded Demos & Walkthroughs | Ryan/Jesse |  | Complete recorded demos including enablement, deprovisioning, and downstream impacts available for async review | Demos available but missing some workflow steps or deprovisioning | No recorded demos or incomplete feature demonstration
Marketing & Positioning | Overall Product Marketing Signoff | Kristin
| Messaging & Positioning | Kristin |  | Value proposition clear, target audience defined, messaging tested | Messaging finalized but limited market validation | Unclear value proposition or target market
| Launch Campaign (if applicable) | Kristin |  | Multi-channel campaign ready, content calendar approved, budget allocated | Campaign planned but execution details being finalized | No comprehensive launch plan or budget approval
| Website/Landing Pages | Kristin |  | Product pages live, SEO optimized, conversion tracking implemented | Pages ready but minor content/design tweaks needed | Critical web presence missing or not functional
| Sales Collateral | Kristin |  | Case studies, white papers, product sheets, videos complete | Most collateral ready, 1-2 items in final review | Insufficient supporting materials for sales process
Revenue Ops | Overall Revenue Ops Signoff | Christa
| Confirmed Pricing Communicated & Documented | Christa |  | Communicated to RevOps for build into SF Pricebook & PandaDoc adjustments (if needed) - Final pricing approved, bundling vs. standalone pricing clear, customer purchase requirements documented | Communicated to RevOps for build into SF Pricebook & PandaDoc adjustments (if needed) with timeline of when it will be finalized so system adjustments can be made. Pricing finalized but packaging details being refined | Pricing strategy not finalized or customer purchase requirements unclear

## Sheet1 (hidden)
Decision Matrix
Department | Criteria | Go | Conditional Go | No Go | Stakeholder
Technical & Product Readiness | Core Functionality | All primary features working as designed, zero critical bugs | Minor non-critical bugs present with workarounds documented | Critical bugs present that impact core user experience
Technical & Product Readiness | Performance & Scalability | Meets all performance benchmarks, load tested for expected traffic | Minor performance issues with mitigation plan in place | Fails to meet performance requirements or scalability concerns
Technical & Product Readiness | Security & Compliance | Security audit complete, all compliance requirements met | Minor security issues with remediation timeline <30 days | Critical security vulnerabilities or compliance gaps
Technical & Product Readiness | Data Migration/Integration | All data migration tested and validated, integrations fully functional | Data migration complete with minor validation issues | Data integrity concerns or integration failures
Technical & Product Readiness | Backup & Recovery | Disaster recovery tested and documented, RTO/RPO requirements met | Backup systems in place but recovery not fully tested | No adequate backup/recovery procedures
Technical & Product Readiness | Technical Documentation
Customer Support Readiness | Knowledge Base | Comprehensive help documentation, FAQs, troubleshooting guides published | Documentation 90%+ complete, minor gaps identified | Significant documentation gaps or not published
Customer Support Readiness | Support Team Training | All support agents trained on product, escalation procedures defined | 80%+ of team trained, knowledge transfer ongoing | Insufficient team training or no escalation process
Customer Support Readiness | Ticketing System | Support workflows configured, SLA definitions set, routing rules active | System configured but minor workflow adjustments needed | Ticketing system not ready or SLAs undefined
Customer Support Readiness | Escalation Procedures | Clear escalation paths to product/engineering teams established | Escalation process defined but not fully tested | No clear escalation procedures
Customer Support Readiness | Support Scripts | Standard responses, troubleshooting scripts, known issue documentation ready | Most scripts ready, minor gaps in edge case scenarios | Inadequate support scripts or procedures
Implementation Readiness | Implementation Methodology | Proven implementation process documented, project templates ready | Process documented but limited field testing | No standardized implementation approach
Implementation Readiness | Technical Documentation | Installation guides, configuration docs, integration specs complete | Documentation 90%+ complete with minor gaps | Critical technical documentation missing
Implementation Readiness | Implementation Team | Certified implementation specialists available, capacity planned | Team mostly ready but may need additional training/resources | Insufficient implementation capacity or expertise
Implementation Readiness | Customer Onboarding | Onboarding process defined, milestone checkpoints established | Process defined but not fully validated with customers | No structured onboarding process
Implementation Readiness | Project Management Tools | PM tools configured, templates ready, tracking mechanisms in place | Tools ready but processes need refinement | No project management infrastructure
Customer Success Readiness | Success Metrics | KPIs defined, measurement tools in place, benchmarks established | Metrics defined but measurement tools being refined | No clear success metrics or measurement plan
Customer Success Readiness | Customer Journey Map | Complete journey mapped, touchpoints defined, success milestones identified | Journey mostly mapped but some touchpoints undefined | No structured customer journey documentation
Customer Success Readiness | Health Scoring | Customer health scoring model defined and automated | Health scoring framework exists but not fully automated | No customer health monitoring system
Customer Success Readiness | Renewal/Expansion Strategy | Renewal process defined, expansion opportunities identified, playbooks ready | Strategy defined but playbooks need development | No renewal or expansion strategy
Customer Success Readiness | Customer Education | Training materials, certification programs, user community ready | Most educational content ready, some gaps remain | Insufficient customer education resources
Sales Readiness | Sales Materials | Complete sales deck, battle cards, ROI calculator, competitive analysis ready | Most materials ready, missing 1-2 non-critical items | Core sales materials incomplete or outdated
Sales Readiness | Pricing & Packaging | Final pricing approved, packaging clearly defined, discount structure established | Pricing finalized but packaging details being refined | Pricing strategy not finalized or approval pending
Sales Readiness | Sales Training | All sales team trained on product, objection handling, demo scripts prepared | 80%+ of sales team trained, remaining scheduled within 1 week | <80% of sales team trained or no training plan
Sales Readiness | Demo Environment | Stable demo environment with realistic data, demo scripts tested | Demo environment available but may have minor issues | Demo environment unreliable or not ready
Sales Readiness | Legal Documents | Contracts, MSAs, SLAs finalized and legally approved | Contracts ready but minor terms under review | Legal documentation incomplete or under review
Marketing Readiness | Messaging & Positioning | Value proposition clear, target audience defined, messaging tested | Messaging finalized but limited market validation | Unclear value proposition or target market
Marketing Readiness | Launch Campaign | Multi-channel campaign ready, content calendar approved, budget allocated | Campaign planned but execution details being finalized | No comprehensive launch plan or budget approval
Marketing Readiness | Website/Landing Pages | Product pages live, SEO optimized, conversion tracking implemented | Pages ready but minor content/design tweaks needed | Critical web presence missing or not functional
Marketing Readiness | Sales Collateral | Case studies, white papers, product sheets, videos complete | Most collateral ready, 1-2 items in final review | Insufficient supporting materials for sales process