## ui-rollout-criteria-import
Category | Label | Rating Stage | Stakeholder | GO Definition | CONDITIONAL GO | NO GO
UX & Research | UX Validation Complete | [name of pod's product manager] | GTM Access |  | Validation plan executed per Impact Level â€” internal product user sessions (3-5), external representative user sessions (5-8 for Impact 1-2), and customer sessions (Impact 1) completed with findings documented and applied | Validation partially complete â€” some required sessions not yet conducted; mitigation plan documented with timeline | Required validation has not been performed for this Impact Level
UX & Research | UX Preview Validated | [name of pod's product manager] | GTM Access |  | UX and Product Education have reviewed changes in UX Preview production group; both signed off on visual accuracy, interaction quality, and documentation needs | Preview available but one or more sign-offs still pending; issues identified with clear resolution plan | No UX Preview group configured or reviews not started
UX & Research | Behavioral Baseline Established | [name of pod's product manager] | GTM Access |  | Baseline Pendo/usage metrics captured for all affected workflows; pre-launch snapshot documented with defined comparison criteria for post-launch analysis | Baseline partially captured â€” some metrics still being instrumented or historical data gaps identified with workaround plan | No behavioral baseline established for affected workflows
Technical Readiness | Feature Gate Readiness | [name of pod's product manager] | Internal Readiness |  | Feature gate implemented and tested; rollback verified in staging with <30 minute recovery time; gate controls validated for all cohort groups (Internal, Cohort 1, Cohort 2) | Feature gate implemented but rollback procedure not yet tested end-to-end; gate configuration documented | No feature gate implemented for an Impact 1-2 change; or gate exists but has not been validated
Technical Readiness | Rollback Plan Ready | [name of pod's product manager] | Internal Readiness |  | Rollback plan documented and tested â€” detection (<15 min), assessment (confirm rollout-related), feature gate disable (<30 min), stakeholder communication (<1 hour); communication template prepared | Rollback plan documented but not yet tested end-to-end; stakeholder communication template in draft | No rollback plan exists or rollback mechanism has not been identified
Enablement & Training Readiness | In-App Education Deployed | smartin@clearcompany.com | Internal Readiness |  | Pendo guides deployed per Impact Level â€” full onboarding experience (Impact 1), guided walkthroughs (Impact 2), or contextual guidance (Impact 3); accessibility reviewed; linked to Zendesk articles where applicable | Pendo guides drafted and in review but not yet deployed to production; or accessibility review pending; Zendesk article updates in progress | Required Pendo guides not created; or guides created but fail accessibility or plain-language review; or no education assets for an Impact 1-3 change
Product Marketing | Customer Communication Plan Executed | kpenney@clearcompany.com | Cohort 1 Live |  | All required customer communications sent per Impact Level timeline â€” advance email (Impact 2: 2-4 weeks; Impact 1: 18+ weeks), CSM strategic account outreach completed (Impact 1), reminder and training resource emails sent | Communication plan exists and is on track but some communications still pending; or minor timeline delays with clear catch-up plan | No customer communication plan for an Impact 1-2 change; or significantly behind required timeline with no mitigation